## Slide 1: RCM-143: Small Diameter High Ratio REPS
Description
    Develop design for 7mm pitch ball circuit on 26mm rack
Motivation : 15
Deliverables
  Procure components for laboratory functional evaluation
    Activity absorbed into REPS efficiency DOE
Timing
  Procure components:
    Ball Nuts: Complete
    Ball Guides: Complete
    Ball Screws: In Process
    Motors: In Process
Team Members/Customers
  P. Kern / Chuck Schlaud
  Customers: Internal development project
Last updated: 26OCT15

## Slide 2
Status Update:
Functional evaluations absorbed into REPS efficiency DOE
  7mm vs. 8mm pitch
  36.4O vs. 45O contact angle
All design and modeling complete (assumes bolt-on driven pulley and Ford C2 application)
Ball screw prototype footprint complete
  Assumes rolled ball track
  Rolling dies are finished
  Racks are in process
Ball return guides are finished
Challenges:
Additional time required for DOE parts (tooling lead time for ball screw)
        Ball guide molding die design will be different from current ball return guides
Next Actions:
Procure parts
Perform DOE
Last updated: 26OCt15
RCM-143: Small Diameter High Ratio REPS