## Slide 1: SE07 – Deploy Formal Safety Process(es)
Description
  Document safety process for engineering and management
  Develop templates and guidelines for work products
  Implement these processes and templates
Motivation (Score X)
  Required for ISO 26262 compliance
Deliverables
  Approved process document in use on a program
  Approved templates and guidelines documents in use on a program
Timing
  SPICE audit prep timeline
    1st Internal audit June 9, 2014
    External audit Jan 5, 2015
  Desire to execute on PSA BMPV/B618
Team Members/Customers
  Kathy Pattok, Safety Team/ Nexteer CPI, Customers

## Slide 2: SE02 – Global Cross Check
Status
  KPIT supporting process and template development
    23 documents planned, received (100%)
    18 documents reviewed once and feedback provided (78%)
    6 documents edited and 2nd draft submitted by KPIT
    1 document reviewed after revisions
    1 document in process of edit by Nexteer into ‘final’ version
      Will deploy on PSA BMPV
Challenges
  Quality of KPIT deliverables
  Time available to review deliverables
Next Steps
  Catch up to timeline
  Nexteer revisions KPIT 2nd drafts to get ‘final’ version
  Consider using KPIT as independent confirmation review of Nexteer edited documents