## Slide 1: SE43 – Limp Home Motor Phase Current Sensor
Description
  Eliminate Loss of Assist for diagnostic failures of a motor phase current sensor.
  Operate system in feedforward torque control mode (voltage mode) during the limp home event.
Motivation (Score: 6.5)
  Some of our customers are requiring this capability today
  More are expected to require this soon
Deliverables
  System, subsystem, and FDD requirements for function.
  Prototype software suitable for customer use on test track.
  Production SW FDD’s.
  Test Plans
Timing
  FDD requirements for PSR complete by May 15, 2014
    PSR Request submitted May 27, 2014
  PSR Software to customer by end of July 2014
    Demo was moved to September 2014
  Ford S550, March 2016 SOP
Team Members/Customers
  Powerpack Systems: Julie Kleinau, Prerit Pramod, Krishna Namburi
  Systems - Functional Safety: Kathy Pattok, Mark Norman
  Customer – Ford S550/P552 PDT

## Slide 2: SE43 – Limp Home Motor Phase Current Sensor
Status
  Requirements completed and released.
  Software implementation and testing complete.
  Management of torque transition study complete and method selected (joint decision with customer).
  Ready for launch with SW09.07.00.
Challenges
  All EA3.x issues resolved.
Next Steps
  Design has been carried over to EA4.x architecture.
  Determine if revisions required due to nature of unique current measurement diagnostics on EA4.x