## Slide 1: CCM-78: Spring Worm Isolators
Description
  Implement spring isolators for production
Motivation : 3.0
Deliverables
  Fix low temperature reversal clunk issue
  Improve robustness (bumper geometry change)
Timing
  Quotes for new bumper geometry by mid May
  Bumper geometry change prototypes by end of June
Team Members/Customers
  Team names: Brad Sundholm
  Customers: Application Teams
Last updated: 01MY15

## Slide 2
Status Update:
Supplier Help
  Asked Parker, Freudenberg, and Mevis supplier for bumper design help
  Parker and Freudenberg have proposals
Bumper Design Testing
  Offset castle design
    Test in vehicle at cold temp
Inner Guide Deformation Issue
  Amount of overlap between components causing deformation found
  Testing ongoing to prevent deformation
Thermal Testing
  Calculations and Testing ongoing
Challenges:
Getting reasonable piece price for new bumper design
Vehicle and vehicle chamber availability
Determine minimum amount of overlap between components required to hold assembly together
Next Actions:
Roadmap worm axis in Fiat 500 system
Build offset castle bumpers in Haitec system
  Test offset castle bumpers at cold temp in vehicle chamber
Last updated: 01MY15
CCM-78: Worm Spring Isolators