## Slide 1: C1XX Plastic Pulley Development
Description
  Development of a plastic pulley to replace metal pulley for REPS gears. Prism is production source since Fall 2014.
Current Status:
  Parts meet print run out of 0.15 – latest grooming has produced parts better than 0.1.
  Design Validation in Process:
    All parts passed High Load Fatigue (tie rod loads of 20.8 kN)
    Bottoming test is running – target completion end of April
    Target Life Test Running – target completion mid April
    Rotational Noise Test proved equivalent to metal pulley
PV starts late April/early May 2015
  PPAPed Single Cavity Stainless Steel Tool
  Target completion of PV is Aug 2015
Production Timing
  Production 4 cav tool nearing completion: First parts targeted end of June
  PPAP Single Cavity end of June 2015
  PV Production tool while running production on Single Cavity – will cover while volumes are low
  SOP December 2015
Team Member/Customers
  Kevin McClendon / David Bell / George Arlt / Nik von Matt