## Slide 1: RCM-143: Small Diameter High Ratio REPS
Description
    Develop design for 7mm pitch ball circuit on 26mm rack
Motivation : XX
Deliverables
  Complete ball screw design and prototype footprint
  Procure components for laboratory functional evaluation
Timing
  Ball Screw Design: 27MR15
  Procure components: 26JN15
Team Members/Customers
  P. Kern
  Customers: Internal development project
Last updated: 25FE15

## Slide 2
Status Update:
Ball nut design and modeling complete (assumes bolt-on driven pulley and Ford C2 application)
Ball screw prototype footprint being developed.
  Assumes ground ball track
  Will also have 8mm pitch parts with ground ball track produced for best comparison
Ball return guide molding die design issues resolved
Challenges:
Additional processing steps for ball screw ground ball track will present challenges
        Stack issues associated with additional processing steps of ball screw will need to be comprehended
        Ball guide molding die development will be different from current ball return guides
Next Actions:
Finish ball screw drawings
Review and finalize ball screw process assumptions
Order parts
Last updated: 25FE15
RCM-143: Small Diameter High Ratio REPS