## Slide 1: CCM-174: Zero-Lash Spur Gear
Description
  Transmits absolute position of worm gear
  Compensates for large tolerance stack up by using increased mesh interferences
Motivation:
Deliverables
  Finalized Design
  Prototypes for Validation
Timing
  Finalized Design – 01JUN16
  VSS 9BUX SOP – 01JAN18
Team Members/Customers
  Team names: Adam Lee/Jeff Beyerlein
  Customers: Sensor Group/Applications
Last updated: 23FEB16

## Slide 2
Status Update:
Initial Design Proposed – 01SEP15
  Prototype Parts Made – 15OCT15
Prototype Testing Started – 18JAN16
  1 life of Durability at 125 C – Pass
  Maintains Accuracy at 125 C – Pass
  1 life of Durability at -40 C – Ongoing
  Maintains Accuracy at -40 C – Ongoing
Design w/ Prod. Features –
  Parts Made –
Challenges:
Quieter than current design, but still has running noise
Molding process that is robust to plastic deformation of small teeth
If design will take up the entire tolerance without preload feature
Next Actions:
Finish Temperature Testing
Propose a new design incorporating production level features
Cost impact analysis
Last updated: 23FEB16
CCM-174: Zero-Lash Spur Gear